## H500项目风险评估与管控表
POTENTIAL
FAILURE MODE AND EFFECTS ANALYSIS
(DESIGN FMEA)
FMEA number：
| Model: |  |  | Design Responsibility: | [5 empty] | Page：
| Core team: |  |  | Key Date: | [5 empty] | Prepared by：
[10 empty] | FMEA Date （Orig.）： |  |  |  | Rev:A
Item | Potential | Potential | Sev.(严重性) | Potential | Occur.(发生率) | Current | Current | Detec.(可发现率) | R.P.N.(风险指数) |  | Responsibility | Action Results
| Failure | Effect(s) of |  | Cause(s)/ | [5 empty] | Recommended | & Target | Actions | Sev | Occ | Det | R.P.N.
| Mode | Failure |  |  |  | Controls | Controls |  |  | Action(s) | Competition | Taken
Function |  |  |  | of Failure |  | Prevention | Detection |  |  |  | Date
(功能模块) | (潜在风险) | (潜在失效影响) |  | (潜在可能原因) |  | (当前控制/预防措施) | (当前测量/侦测/发现办法) |  |  | (需采取何动作) | (谁负责跟进) | (已采取何动作)
1、ID/MD | 手写笔的固定方式，影响用户体验及笔的保护。 | 笔如果固定不好，可靠性对其冲击影响较大。 | 6 | 不了解此笔的可靠性如何。 | 4 | 结构设计尽量保护好此笔，与供应商了解具体的可靠性问题。 | 结构设计尽量保护好此笔，与供应商了解具体的可靠性问题。 | 3 | 72
| 皮套的结构方式及整体工艺（供应商能力）是否能达到上档次的效果，影响用户体验。 | 皮套材料的选择，影响整机档次。 |  | 供应商资源，是否能制作及提供较好的真皮材料。 |  | 与供应商沟通，落实。 | 与供应商沟通，落实。
| A壳变形量可能较大，影响CTP屏和LCD的保护效果。 | A壳变形，最终影响到CTP屏和LCD屏的保护。 |  | 因为ID表面要做NCVM处理，则A壳不能用加玻纤的材料，则变形量不好近控制。 |  | 优化结构设计，增加A壳强度，使不加玻纤也不变形。 | 优化结构设计，增加A壳强度，使不加玻纤也不变形。
| 包括ID、堆叠（２８日定案）、手写笔的固定，未最终确定，结构设计的调整，可能影响最终结构设计完成的时间。 | 影响11/29的开模时间。 |  | 影响11/29的开模时间。 |  | 合理安排资料，全力完成结构设计。 | 合理安排资料，全力完成结构设计。